## Sheet1
BUGS
Title | Description | Reproducible Steps | Severity | Priority | Affected devices | OS version | App version | Expected Result | Network | Attachments
Change account didn't work after navigating from schedule screen | As a user when i try to add an income and go to schedule and back again and try to change the account, the button not work properly | 1- From Home Screen click on income or expense button 2- Click on schedule button at the top 3- Then back again to income/expense screen 4-Try to click on account change button | Major | High | iOS (iphone 11) | 14.5.1 | 1.3.18 | When the user clicks on change payment method the button should work properly | Wifi | https://drive.google.com/file/d/1-b5BTGt9ZwkP-D8uaeslg3WBDQXi2ycK/view?usp=sharing
After Deleting an account , it still appear in editing transaction history | As a user when i made a transaction from account A to Account B , then i delete account B , then go to transaction history the account B still exist and can transfer an amount to it . | 1- From Home Screen click on transfer button 2- Transfer an amount from account A to account B 3- Go to Accounts and delete account B 4- Then From Home page click on transaction history and click on the previous transaction 5- Try to change transaction from B to A and also increase or decrease the amount | Major | medium | iOS (iphone 11) | 14.5.1 | 1.3.18 | When the user deletes an account all previous transactions should be dimmed or not be editable and selecting deleting account is not an optional | Wifi | https://drive.google.com/file/d/1E07TolBxAe65aWoX22-WFhobYS8nDPcN/view?usp=sharing
Currency sheet occupying all the screen height | As a user when i try to change my account currency the currency sheet popup and occuping the whole screen which blocks me to make any something else | 1- From Home page click on 3 dots from top right 2- From menu appeared click on settings 3- Click on the value of currency | Minor | low | iOS (iphone 11) | 14.5.1 | 1.3.17 | When the user deletes an account all previous transactions should be dimmed or not be editable and selecting deleting account is not an optional | Wifi | https://drive.google.com/file/d/1jSufoy1DRdxWjPJZYJbFKKbIv5JHEY4A/view?usp=sharing
Headers are written in english in generated excel sheet even the language is changed | As a user when i select any language rather than english and try to extract excel sheet , the headers still in english language | 1- Change the language of app to itialian (for example) 2- Go to Settings section and select export excel sheet 3- After file extracted open it | Major | high | iOS(iphone 11) Android (Samsung J7) | 14.5.1 6.0.1 | 1.3.18 | The header should be also written in same language | Wifi | https://drive.google.com/file/d/1bh4arvzq1hqoqXEOxZvNNnfoifekf_LS/view?usp=sharing
Catgory can be used even user disable it | As a user when i disable a category , it still appear in home screen so that it can be used again | 1- From Home screen select communication as an expenses 2- Go to Category Screen and disable communication 3- Go to Home screen and try to click on commincation 4- Then you can add expenses as a communication | Major | medium | iOS(iphone 11) Android (Samsung J7) | 14.5.1 6.0.1 | 1.13.18 | The add expense as a communication should be dimmed | Wifi | https://drive.google.com/file/d/151qp-ymwsYv5wnTa8rFfOWFiIB_WkzNO/view?usp=sharing
App crashes while opening it | As a user when i open the app and leave it for a while it crashes | 1- Open the App 2- Leave it for a while | Critical | high | Android. (pixel 3a) | 11 | 1.13.18 | The app should work without crashes | wifi
Some expenses with low percentage have no line connected with the circle | As a user when i adding multiple expenses with high and low percentage , i notice that some of low percentage expenses has no lines connected | 1- Add Expenses with high value with (30000) for example 2- Add another expenses with low value (10) for example | Minor | low | iOS(iphone 11) Android (Samsung J7) | 14.5.1 6.0.1 | 1.13.18 | Each expense should connect with the circle | Wifi | https://drive.google.com/file/d/1R7QhRZQk2PzEICYgZHEwzUpZSB-BID06/view?usp=sharing
Start day should be related with Month days (not all months have 31 days) | As a user when i select a day of Month , the value of the day shoulde be related to the month days | 1- Select Month with 30 day 2- Open Settings menu and select start day | Minor | low | iOS(iphone 11) Android (Samsung J7) | 14.5.1 6.0.1 | 1.13.18 | The max day should be 30 not 31 | Wifi | https://drive.google.com/file/d/1hSIxqUUoUqeU95PQlLWDf6vmEzVRK99p/view?usp=sharing
Some lines overlap with each others when adding a lot of expense during long period (one month) | As a user when i added some expenses over month for example , i see lines overlap each other | 1- Add a lot of expenses in different days 2- Filter with month | Minor | low | iOS(iphone 11) Android (Samsung J7) | 14.5.1 6.0.1 | 1.13.18 | Each line should not overlap with each other | Wifi | https://drive.google.com/file/d/155Sret5EhwalyRWtR8NzBwGKmmf28ERh/view?usp=sharing
Enhancements
Text when account has no records needed to include also this account along with this period |  | 1- From the Home page select account has no records 2- Then click on history section | Minor | low | iOS(iphone 11) Android (Samsung J7) | 14.5.1 6.0.1 | 1.13.18 | The text should indicate that there is no record for this period and also for this account | Wifi | https://drive.google.com/file/d/1hGmcbYMyMJcpvOuABju1r36oa1OFLJSY/view?usp=sharing
User cannot change the transfer direction after clicking on amount field , so he must go to previous screen and return back to the same screen |  | 1- From Home page , click on transfer buttom 2- After selecting two accounts , click on amount text field 3- Try to change the two accounts selected | Minor | low | iOS (iphone 11) | 14.5.1 | 1.13.18 | The user can be click on anywhere to edit the select accounts without going back | Wifi | https://drive.google.com/file/d/1JxrhjdEnBjJzApYxgh3sYrtqiI8g49yO/view?usp=sharing
User cannot detect that negative amount in balance is represented between two brackets |  | 1- From Home page click on expense button 2- Try to add value more than incomes | Minor | low | iOS (iphone 11) | 14.5.1 | 1.13.18 | The balance should be represented with negative sign | Wifi | https://drive.google.com/file/d/1E7pqU5HcfH8kAfPmqsfATHGl-28AaSls/view?usp=sharing
It's better to make a default selected image when adding new account |  | 1- From Home page click on 3 dots from top right 2- From menu appeared click on Accounts 3- Click on Add button then Account screen will open 4- Add a new name for the account and press add | Minor | low | Android(Samsung J7) | 6.0.1 | 1.13.18 | The account should be added automatically like the iOS platform | Wifi | https://drive.google.com/file/d/1Fe9ODQ7_Y8vEMwcz6D6TCgBYr8g3_yIx/view?usp=sharing
Arabic Currency right aligned |  | 1- Go to Currency section and choose Saudi Ryal | Minor | low | iOS | 14.5.1 | 1.13.18 | Arabic Currency should be left aligned | Wifi | https://drive.google.com/file/d/1FF8FWIUWvjdrtIdwHU9rU1tVNJyKk465/view?usp=sharing
There should be a handeling a large numbers with cuurency and balance word |  | 1- Add large amount as an expense 2- Change language to french for example | Minor | low | iOS(iphone 11) Android (Samsung J7) | 14.5.1 6.0.1 | 1.13.18 | The design should be more clear | Wifi | https://drive.google.com/file/d/1KilI2d3Qx-ZscpypptImn5bJxRQifb8O/view?usp=sharing